## Sheet1
Sl. No. | Delivery Item | Expected Date | Actual Date | Comments
1 | UAA setup for Locomotive application | 2016-02-05 | 2016-02-05 | Lost 1 days of work due to space cleanup by Bill
2 | locomotive-dataingestion-service | 2016-02-16 | 2016-02-12
3 | locomotive-simulator-service | 2016-02-16 | 2016-02-12
4 | locomotive-client-service (Rest Client endpoint) | 2016-02-19 | 2016-02-19
5 | locomotive-predix-seed (UI) | 2016-02-26 | 2016-02-25 | Integrated Asset service and TimeSeries with Login authentication along with graph chart
6 | ACS | 2016-02-29 | 2016-02-25 | Integrating ACS with UI is not possible as the token generated by UI is not ACS compliant
7 | Documentation | 2016-02-29 | 2016-02-29
NB: | All the code and deliverables are uploaded in public github.Path::>>https://github.com/romit7/TCS-Loc-Training